## Task_Table
ID | Active | Name | Duration | Start | Finish | Predecessors | Resource Names | Outline Level | Notes
0 | Yes | Drone-Car Software Development | 162 days | January 6, 2023 8:00 AM | August 22, 2023 8:00 AM |  |  | 0
1 | Yes | Project Initiation | 0 days | January 6, 2023 8:00 AM | January 6, 2023 8:00 AM |  |  | 1
2 | Yes | Phase I - Project Specification | 7 days | February 6, 2023 8:00 AM | February 15, 2023 8:00 AM |  |  | 1 | The complete requirements document will need to be written up and presented on March 22nd or 29th (after your project plan is complete). Your team will be expected to do a 12-minute presentation (powerpoint or equivalent) of the phase 1 artifacts on 2/15/
3 | Yes | Section 1.0 Intro/Scope | 1.75 days | February 6, 2023 8:00 AM | February 7, 2023 3:00 PM |  | Demetrius Johnson,Jonathan Schall,Olivia Pelligrini,Ryan Sauer | 2
4 | Yes | Section 2.0 Usage Scenario | 7 days | February 6, 2023 8:00 AM | February 14, 2023 5:00 PM | 3SS | Ryan Sauer | 2
5 | Yes | Sections 4.1 Descrip. For Function n | 7 days | February 6, 2023 8:00 AM | February 14, 2023 5:00 PM | 3SS | Demetrius Johnson,Jonathan Schall,Olivia Pelligrini,Ryan Sauer | 2
6 | Yes | Section 4.3 Use Case Diagram | 7 days | February 6, 2023 8:00 AM | February 14, 2023 5:00 PM | 3SS | Olivia Pelligrini | 2
7 | Yes | Section 8.1 System Traceability matrix | 7 days | February 6, 2023 8:00 AM | February 14, 2023 5:00 PM | 3SS | Jonathan Schall | 2
8 | Yes | Section 9.0 References | 7 days | February 6, 2023 8:00 AM | February 14, 2023 5:00 PM | 3SS | Demetrius Johnson | 2
9 | Yes | Project Team Checkin #1 | 0 days | February 8, 2023 8:00 AM | February 8, 2023 8:00 AM | 8SS |  | 2
10 | Yes | Phase I - Project Specs Complete | 0 days | February 14, 2023 5:00 PM | February 14, 2023 5:00 PM | 8 |  | 2
11 | Yes | Present Phase I in class | 0 days | February 15, 2023 8:00 AM | February 15, 2023 8:00 AM | 10 |  | 2 | The complete requirements document will need to be written up and presented on March 22nd or 29th (after your project plan is complete). Your team will be expected to do a 12-minute presentation (powerpoint or equivalent) of the phase 1 artifacts on 2/15/
12 | Yes | Phase II - Project Specification | 26 days | February 15, 2023 8:00 AM | March 22, 2023 5:00 PM |  |  | 1 | The complete requirements document will need to be written up and presented on March 22nd or 29th (after your project plan is complete). Your team will be expected to do a 12-minute presentation (powerpoint or equivalent) of the phase 1 artifacts on 2/15/
13 | Yes | Project Team Checkin #2 | 0 days | February 22, 2023 8:00 AM | February 22, 2023 8:00 AM | 11 |  | 2
14 | Yes | Section 3.0 Data Model and Descrip. | 4 days | February 15, 2023 8:00 AM | February 20, 2023 5:00 PM | 11 | Ryan Sauer | 2
15 | Yes | Section 4.2 - Software Interface Descrip. | 4 days | February 21, 2023 8:00 AM | February 24, 2023 5:00 PM | 14 | Jonathan Schall | 2
16 | Yes | Section 4.4 Sequence Diagrams | 4 days | February 27, 2023 8:00 AM | March 2, 2023 5:00 PM | 15 | Olivia Pelligrini | 2
17 | Yes | Section 4.5 Collab. and Comm. Diagrams | 4 days | March 3, 2023 8:00 AM | March 8, 2023 5:00 PM | 16 | Jonathan Schall | 2
18 | Yes | Section 5.0 Behavioral Model and Descrip. | 4 days | March 9, 2023 8:00 AM | March 14, 2023 5:00 PM | 17 | Olivia Pelligrini | 2
19 | Yes | Section 6.0 Restric. Lim. And Restraints | 2 days | March 15, 2023 8:00 AM | March 16, 2023 5:00 PM | 18 | Jonathan Schall | 2
20 | Yes | Section 7.0 Validation Criteria | 4 days | March 17, 2023 8:00 AM | March 22, 2023 5:00 PM | 19 | Ryan Sauer | 2
21 | Yes | Draft Poster Due March 8th | 11 days | February 22, 2023 8:00 AM | March 8, 2023 5:00 PM | 13SS |  | 2 | Your team is required to create poster using the new HYPERLINK "https://canvas.umd.umich.edu/courses/529695/files/42781562?wrap=1"CIS - Electronic Poster Template.pptxHYPERLINK "https://canvas.umd.umich.edu/courses/529695/files/42781562/download?download_
22 | Yes | Project Plan and RMMM Due March 8th | 11 days | February 22, 2023 8:00 AM | March 8, 2023 5:00 PM | 13SS |  | 2 | CIS 4951/4961/4971/4981 Planning Document Winter 2023...
23 | Yes | Phase II - Project Specs Complete | 0 days | March 22, 2023 5:00 PM | March 22, 2023 5:00 PM | 20 |  | 2
24 | Yes | Present Phase II in class (DUE MARCH 22 OR 29TH) | 0 days | March 22, 2023 5:00 PM | March 22, 2023 5:00 PM | 23 |  | 2 | The complete requirements document will need to be written up and presented on March 22nd or 29th (after your project plan is complete). Your team will be expected to do a 12-minute presentation (powerpoint or equivalent) of the phase 1 artifacts on 2/15/
25 | Yes | Project Team Check In #3 | 0 days | March 22, 2023 5:00 PM | March 22, 2023 5:00 PM | 24 |  | 2
26 | Yes | Design (Modify/update project Specs) | 20 days | February 15, 2023 8:00 AM | March 14, 2023 5:00 PM |  |  | 1
27 | Yes | Review preliminary software specifications | 4 wks | February 15, 2023 8:00 AM | March 14, 2023 5:00 PM | 8 |  | 2
28 | Yes | Develop functional specifications | 4 wks | February 15, 2023 8:00 AM | March 14, 2023 5:00 PM | 27SS |  | 2
29 | Yes | Develop prototype based on functional specifications | 4 wks | February 15, 2023 8:00 AM | March 14, 2023 5:00 PM | 27SS |  | 2 | Design a drone-car model scenario to test our drone-car collaboration program's performance metrics (latency, battery life, etc.)....
30 | Yes | Review functional specifications | 4 wks | February 15, 2023 8:00 AM | March 14, 2023 5:00 PM | 27SS |  | 2
31 | Yes | Develop Testing Environment and Metric Collection | 2 wks | February 15, 2023 8:00 AM | February 28, 2023 5:00 PM | 27SS | Ryan Sauer | 2
32 | Yes | Design Complete | 0 days | February 28, 2023 5:00 PM | February 28, 2023 5:00 PM | 31 |  | 2
33 | Yes | Development | 60 days | January 6, 2023 8:00 AM | March 30, 2023 5:00 PM |  |  | 1
34 | Yes | Review functional specifications | 2 days | March 15, 2023 8:00 AM | March 16, 2023 5:00 PM | 30 |  | 2
35 | Yes | Build Clover 4.2 Drone | 2 wks | January 6, 2023 8:00 AM | January 19, 2023 5:00 PM | 1SS | Demetrius Johnson | 2
36 | Yes | Drone sensor calibration (Q Ground Control) | 3 wks | January 20, 2023 8:00 AM | February 9, 2023 5:00 PM | 35 | Demetrius Johnson | 2
37 | Yes | Successfully Manually fly Drone | 0 days | February 9, 2023 5:00 PM | February 9, 2023 5:00 PM | 36 | Demetrius Johnson | 2
38 | Yes | Build PiCar-X Car | 1 wk | February 10, 2023 8:00 AM | February 16, 2023 5:00 PM | 37 | Demetrius Johnson | 2
39 | Yes | Car sensor calibration | 1 wk | February 17, 2023 8:00 AM | February 23, 2023 5:00 PM | 38 | Demetrius Johnson | 2
40 | Yes | Successfully manually control car with Web Contr Interface | 0 days | February 23, 2023 5:00 PM | February 23, 2023 5:00 PM | 39 | Demetrius Johnson | 2
41 | Yes | Learn Drone Simulation Prog Interface | 3 wks | February 10, 2023 8:00 AM | March 2, 2023 5:00 PM | 37SS | Demetrius Johnson | 2
42 | Yes | Learn Drone Programming IDE interface | 3 wks | February 10, 2023 8:00 AM | March 2, 2023 5:00 PM | 37SS | Demetrius Johnson | 2
43 | Yes | Learn Drone vision system interface | 3 wks | February 10, 2023 8:00 AM | March 2, 2023 5:00 PM | 37SS | Demetrius Johnson | 2
44 | Yes | Write basic program in drone-vision simulation | 1 wk | March 3, 2023 8:00 AM | March 9, 2023 5:00 PM | 43 | Demetrius Johnson | 2
45 | Yes | Run basic drone-vision program in real environment | 0 days | March 9, 2023 5:00 PM | March 9, 2023 5:00 PM | 44 | Demetrius Johnson | 2
46 | Yes | Learn Car Programming IDE interface | 1 wk | March 10, 2023 8:00 AM | March 16, 2023 5:00 PM | 45 | Demetrius Johnson | 2
47 | Yes | Learn Car vision system interface | 1 wk | March 17, 2023 8:00 AM | March 23, 2023 5:00 PM | 46 | Demetrius Johnson | 2
48 | Yes | Run basic car-vision program in real environment | 0 days | March 23, 2023 5:00 PM | March 23, 2023 5:00 PM | 47 | Demetrius Johnson | 2
49 | Yes | Process test images in python Open CV to detect red object | 1 wk | February 17, 2023 8:00 AM | February 23, 2023 5:00 PM | 38 | Jonathan Schall,Olivia Pelligrini | 2
50 | Yes | Work with python vision system libraries in drone | 1.33 wks | February 24, 2023 8:00 AM | March 6, 2023 2:20 PM | 49 | Jonathan Schall,Olivia Pelligrini,Demetrius Johnson | 2
51 | Yes | Work with python vision system libraries in car | 2 wks | February 24, 2023 8:00 AM | March 9, 2023 5:00 PM | 49 | Demetrius Johnson,Jonathan Schall,Olivia Pelligrini | 2
52 | Yes | Develop red obstacle vision detection program | 2 wks | March 10, 2023 8:00 AM | March 23, 2023 5:00 PM | 51 | Jonathan Schall,Olivia Pelligrini | 2
53 | Yes | Deploy red obstacle vision progam in drone | 1 wk | March 24, 2023 8:00 AM | March 30, 2023 5:00 PM | 52 |  | 2
54 | Yes | Deploy red obstacle vision progam in car | 1 wk | March 24, 2023 8:00 AM | March 30, 2023 5:00 PM | 52 |  | 2
55 | Yes | Develop communications between drone and car | 6 wks | February 17, 2023 8:00 AM | March 30, 2023 5:00 PM | 38 | Ryan Sauer | 2
56 | Yes | Development complete | 0 days | March 30, 2023 5:00 PM | March 30, 2023 5:00 PM | 55 |  | 2
57 | Yes | Final Poster Due for Submission April 7th (DUE MARCH 31 ON CANVAS) | 10 days | March 17, 2023 8:00 AM | March 30, 2023 5:00 PM | 46 |  | 2 | Important dates – subject to change:...
58 | Yes | Testing | 85 days | March 31, 2023 8:00 AM | July 27, 2023 5:00 PM |  |  | 1
59 | Yes | Testing Development | 40 days | March 31, 2023 8:00 AM | May 25, 2023 5:00 PM |  |  | 2
60 | Yes | Develop code for metric collection interface/method (bandwidth, latency, battery life) | 2 wks | March 31, 2023 8:00 AM | April 13, 2023 5:00 PM | 56 | Ryan Sauer | 3
61 | Yes | Develop car-only-compute automated test environment | 2 wks | April 14, 2023 8:00 AM | April 27, 2023 5:00 PM | 60 | Ryan Sauer | 3
62 | Yes | Develop drone-only-compute test environment | 2 wks | April 28, 2023 8:00 AM | May 11, 2023 5:00 PM | 61 | Ryan Sauer | 3
63 | Yes | Develop drone-car-compute integration test env. | 2 wks | May 12, 2023 8:00 AM | May 25, 2023 5:00 PM | 62 | Ryan Sauer | 3
64 | Yes | APRIL 14TH SENIOR DESIGN COMP! | 0 days | April 14, 2023 8:00 AM | April 14, 2023 8:00 AM | 56 |  | 3 | Important dates – subject to change:...
65 | Yes | Unit Testing | 25 days | May 26, 2023 8:00 AM | June 29, 2023 5:00 PM |  |  | 2
66 | Yes | Review drone code modules | 1 wk | May 26, 2023 8:00 AM | June 1, 2023 5:00 PM | 63 |  | 3
67 | Yes | Review car code modules | 1 wk | May 26, 2023 8:00 AM | June 1, 2023 5:00 PM | 66SS |  | 3
68 | Yes | Review the automated testing environment | 1 wk | May 26, 2023 8:00 AM | June 1, 2023 5:00 PM | 66SS |  | 3
69 | Yes | Modify code | 2 wks | June 2, 2023 8:00 AM | June 15, 2023 5:00 PM | 68 |  | 3
70 | Yes | Re-test modified code | 2 wks | June 16, 2023 8:00 AM | June 29, 2023 5:00 PM | 69 |  | 3
71 | Yes | Unit testing complete | 0 days | June 29, 2023 5:00 PM | June 29, 2023 5:00 PM | 70 |  | 3
72 | Yes | Integration Testing | 20 days | June 30, 2023 8:00 AM | July 27, 2023 5:00 PM |  |  | 2
73 | Yes | Test module integration | 2 wks | June 30, 2023 8:00 AM | July 13, 2023 5:00 PM | 71 |  | 3
74 | Yes | Modify code | 1 wk | July 14, 2023 8:00 AM | July 20, 2023 5:00 PM | 73 |  | 3
75 | Yes | Re-test modified code | 1 wk | July 21, 2023 8:00 AM | July 27, 2023 5:00 PM | 74 |  | 3
76 | Yes | Drone-car load balance Integration testing complete | 0 days | July 27, 2023 5:00 PM | July 27, 2023 5:00 PM | 75 |  | 3
77 | Yes | Results Evaluation | 12 days | July 28, 2023 8:00 AM | August 14, 2023 5:00 PM |  |  | 1
78 | Yes | Deploy software | 1 wk | July 28, 2023 8:00 AM | August 3, 2023 5:00 PM | 76 |  | 2
79 | Yes | Obtain client (Dr. Zheng Song) feedback | 2 days | August 4, 2023 8:00 AM | August 7, 2023 5:00 PM | 78 |  | 2
80 | Yes | Evaluate testing information | 1 wk | August 8, 2023 8:00 AM | August 14, 2023 5:00 PM | 79 |  | 2
81 | Yes | Pilot complete | 0 days | August 14, 2023 5:00 PM | August 14, 2023 5:00 PM | 80 |  | 2
82 | Yes | Post Implementation Review | 1 day | August 15, 2023 8:00 AM | August 15, 2023 5:00 PM |  |  | 1
83 | Yes | Document lessons learned | 1 day | August 15, 2023 8:00 AM | August 15, 2023 5:00 PM | 81 |  | 2
84 | Yes | Post implementation review complete | 0 days | August 15, 2023 5:00 PM | August 15, 2023 5:00 PM | 83 |  | 2
85 | Yes | Drone-Car Project Completed! | 0 days | August 15, 2023 5:00 PM | August 15, 2023 5:00 PM | 84 |  | 1 | SUMMER 2023 FULL SEMESTER: Final day of classes is August 14, last day of exams is August 22nd!
86 | Yes | AUGUST 15TH CLASSES END SUMMER FULL | 0 days | August 15, 2023 5:00 PM | August 15, 2023 5:00 PM | 84 |  | 1
87 | Yes | AUGUST 22ND SEMESTER ENDS | 0 days | August 22, 2023 8:00 AM | August 22, 2023 8:00 AM | 86 |  | 1

## Resource_Table
ID | Name | Type | Material Label | Group | Email Address | User Logon Account | Resource Names | Max Units | Standard Rate | Cost Per Use | Notes
0 |  | Work | [5 empty] | 100% | $0.00/h | 0
1 | Demetrius Johnson | Work |  | Drone-Car Engineer |  |  |  | 100% | $0.00/h | 0
2 | Ryan Sauer | Work |  | Network Engineer |  |  |  | 100% | $0.00/h | 0
3 | Olivia Pelligrini | Work |  | Open CV Image Processing Engineer |  |  | Demetrius Johnson,Jonathan Schall,Olivia Pelligrini,Ryan Sauer | 100% | $0.00/h | 0
4 | Jonathan Schall | Work |  | Open CV Image Processing Engineer |  |  | Ryan Sauer | 100% | $0.00/h | 0
Demetrius Johnson,Jonathan Schall,Olivia Pelligrini,Ryan Sauer
Olivia Pelligrini
Jonathan Schall
Demetrius Johnson
Ryan Sauer
Jonathan Schall
Olivia Pelligrini
Jonathan Schall
Olivia Pelligrini
Jonathan Schall
Ryan Sauer
Ryan Sauer
Demetrius Johnson
Demetrius Johnson
Demetrius Johnson
Demetrius Johnson
Demetrius Johnson
Demetrius Johnson
Demetrius Johnson
Demetrius Johnson
Demetrius Johnson
Demetrius Johnson
Demetrius Johnson
Demetrius Johnson
Demetrius Johnson
Demetrius Johnson
Jonathan Schall,Olivia Pelligrini
Jonathan Schall,Olivia Pelligrini,Demetrius Johnson
Demetrius Johnson,Jonathan Schall,Olivia Pelligrini
Jonathan Schall,Olivia Pelligrini
Ryan Sauer
Ryan Sauer
Ryan Sauer
Ryan Sauer
Ryan Sauer

## Assignment_Table
Task Name | Resource Name | Work | Units | Resource Names
Section 1.0 Intro/Scope | Demetrius Johnson | 14h | 100%
Section 1.0 Intro/Scope | Jonathan Schall | 14h | 100%
Section 1.0 Intro/Scope | Olivia Pelligrini | 14h | 100%
Section 1.0 Intro/Scope | Ryan Sauer | 14h | 100% | Demetrius Johnson,Jonathan Schall,Olivia Pelligrini,Ryan Sauer
Section 2.0 Usage Scenario | Ryan Sauer | 56h | 100% | Ryan Sauer
Sections 4.1 Descrip. For Function n | Demetrius Johnson | 56h | 100% | Demetrius Johnson,Jonathan Schall,Olivia Pelligrini,Ryan Sauer
Sections 4.1 Descrip. For Function n | Jonathan Schall | 56h | 100% | Olivia Pelligrini
Sections 4.1 Descrip. For Function n | Olivia Pelligrini | 56h | 100% | Jonathan Schall
Sections 4.1 Descrip. For Function n | Ryan Sauer | 56h | 100% | Demetrius Johnson
Section 4.3 Use Case Diagram | Olivia Pelligrini | 56h | 100%
Section 8.1 System Traceability matrix | Jonathan Schall | 56h | 100%
Section 9.0 References | Demetrius Johnson | 56h | 100%
Section 3.0 Data Model and Descrip. | Ryan Sauer | 32h | 100%
Section 4.2 - Software Interface Descrip. | Jonathan Schall | 32h | 100%
Section 4.4 Sequence Diagrams | Olivia Pelligrini | 32h | 100% | Ryan Sauer
Section 4.5 Collab. and Comm. Diagrams | Jonathan Schall | 32h | 100% | Jonathan Schall
Section 5.0 Behavioral Model and Descrip. | Olivia Pelligrini | 32h | 100% | Olivia Pelligrini
Section 6.0 Restric. Lim. And Restraints | Jonathan Schall | 16h | 100% | Jonathan Schall
Section 7.0 Validation Criteria | Ryan Sauer | 32h | 100% | Olivia Pelligrini
Develop Testing Environment and Metric Collection | Ryan Sauer | 80h | 100% | Jonathan Schall
Build Clover 4.2 Drone | Demetrius Johnson | 80h | 100% | Ryan Sauer
Drone sensor calibration (Q Ground Control) | Demetrius Johnson | 120h | 100%
Successfully Manually fly Drone | Demetrius Johnson | 0h | 100%
Build PiCar-X Car | Demetrius Johnson | 40h | 100%
Car sensor calibration | Demetrius Johnson | 40h | 100%
Successfully manually control car with Web Contr Interface | Demetrius Johnson | 0h | 100%
Learn Drone Simulation Prog Interface | Demetrius Johnson | 120h | 100%
Learn Drone Programming IDE interface | Demetrius Johnson | 120h | 100%
Learn Drone vision system interface | Demetrius Johnson | 120h | 100%
Write basic program in drone-vision simulation | Demetrius Johnson | 40h | 100%
Run basic drone-vision program in real environment | Demetrius Johnson | 0h | 100%
Learn Car Programming IDE interface | Demetrius Johnson | 40h | 100% | Ryan Sauer
Learn Car vision system interface | Demetrius Johnson | 40h | 100%
Run basic car-vision program in real environment | Demetrius Johnson | 0h | 100%
Process test images in python Open CV to detect red object | Jonathan Schall | 40h | 100%
Process test images in python Open CV to detect red object | Olivia Pelligrini | 40h | 100% | Demetrius Johnson
Work with python vision system libraries in drone | Jonathan Schall | 53.33h | 100% | Demetrius Johnson
Work with python vision system libraries in drone | Olivia Pelligrini | 53.33h | 100% | Demetrius Johnson
Work with python vision system libraries in drone | Demetrius Johnson | 53.33h | 100% | Demetrius Johnson
Work with python vision system libraries in car | Demetrius Johnson | 80h | 100% | Demetrius Johnson
Work with python vision system libraries in car | Jonathan Schall | 80h | 100% | Demetrius Johnson
Work with python vision system libraries in car | Olivia Pelligrini | 80h | 100% | Demetrius Johnson
Develop red obstacle vision detection program | Jonathan Schall | 80h | 100% | Demetrius Johnson
Develop red obstacle vision detection program | Olivia Pelligrini | 80h | 100% | Demetrius Johnson
Develop communications between drone and car | Ryan Sauer | 240h | 100% | Demetrius Johnson
Develop code for metric collection interface/method (bandwidth, latency, battery life) | Ryan Sauer | 80h | 100% | Demetrius Johnson
Develop car-only-compute automated test environment | Ryan Sauer | 80h | 100% | Demetrius Johnson
Develop drone-only-compute test environment | Ryan Sauer | 80h | 100% | Demetrius Johnson
Develop drone-car-compute integration test env. | Ryan Sauer | 80h | 100% | Demetrius Johnson
Document lessons learned | Ryan Sauer | 8h | 100% | Jonathan Schall,Olivia Pelligrini
Jonathan Schall,Olivia Pelligrini,Demetrius Johnson
Demetrius Johnson,Jonathan Schall,Olivia Pelligrini
Jonathan Schall,Olivia Pelligrini
Ryan Sauer
Ryan Sauer
Ryan Sauer
Ryan Sauer
Ryan Sauer